## Sheet1
Sr No | TASKS | Assigned to | Assisted by | Deadline | Status
1 | Project Idea brain-storming | Adarsh |  | 2017-04-07 | Done
Akhil
Ankit
Divya
Amulya
Sandesh
Nithya
2 | Developing Questionnaire | Akhil |  | 2017-04-11 | Done
Sandesh
3 | Conduct Interviews | Adarsh |  | 2017-04-24 | In-Progress
Akhil
Sandesh
4 | Conduct Interviews | Adarsh |  | 2017-04-25 | Done
Akhil
Sandesh
5 | Evaluation of interviews | Adarsh |  | 2017-04-26 | Done
Akhil
Sandesh
6 | MoSCoW Analysis | Sandesh |  | 2017-04-28 | Done
7 | User stories 1 | Amulya | Adarsh | 2017-05-01 | Done
|  | Akhil | Ankit
|  | Sandesh | Nithya
8 | User Stories 2 | Amulya | Nithya | 2017-05-02 | Done
9 | Low-fi prototype 1 | Adarsh |  | 2017-05-03 | Done
Akhil
Sandesh
10 | Low-fi prototype 2 | Amulya | Nithya | 2017-05-04 | Done
11 | Documentation | Akhil | Sandesh | 2017-05-04 | In-Progress
Adarsh
12 | Hifi Prototype 1 | Divya |  | 2017-05-04 | In-Progress
Ankit
13 | Hi-fi Prototype 1 | Divya |  | 2017-05-05 | Done
Ankit
14 | Testing 1 | Sandesh |  | 2017-05-05 | Done
15 | Hifi Prototype 2 | Divya |  | 2017-05-06 | In-Progress
Ankit
16 | Hi-fi Prototype 2 | Divya |  | 2017-05-07 | Done
Ankit
17 | Testing 2 | Sandesh |  | 2017-05-07 | Done
18 | Hifi-Prototype final | Divya |  | 2017-05-08 | Done
Ankit
19 | User experience map 1 | Nithya |  | 2017-05-09 | Done
20 | User experience map final | Adarsh |  | 2017-05-09 | Done
21 | Final Documentation | Akhil |  | 2017-05-10 | Done
Adarsh
22 | Final Documentation | Akhil | Sandesh | 2017-05-11 | Done
Adarsh